## Gantt Chart
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | Simpler Banking Application
PROJECT MANAGER | Ben Webb
COMPANY NAME
DATE | 2024-01-31
[7 empty] | MONTH ONE | [19 empty] | MONTH TWO | [19 empty] | MONTH THREE | [19 empty] | MONTH FOUR
TASK | TASK | TASK | START | COMPLETION | DURATION | PCT OF TASK | W1 - 31st Jan |  |  |  |  | W2 - 7th Feb |  |  |  |  | W3 - 14th Feb |  |  |  |  | W4 - 21st Feb |  |  |  |  | W5 - 28th Feb |  |  |  |  | W6 - 6th March |  |  |  |  | W7 - 13th March |  |  |  |  | W8 - 20th March |  |  |  |  | W9 - 27th March |  |  |  |  | W10 - 3rd April |  |  |  |  | W11 - 10th April |  |  |  |  | W12 - 17th April |  |  |  |  | W13 - 24th April |  |  |  |  | W14 - 1st May |  |  |  |  | W15 - 8th May
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T
1 | Account Management
1.1 | Create and set up a new banking account (Personal/Business). | Filip Obajtek | 2024-01-31 | 2024-03-05 | 34 | 100%
1.2 | Edit account details (e.g., user information, account type). | Filip Obajtek | 2024-03-27 | 2024-05-07 | 41 | 100%
1.3 | Close an account. | Filip Obajtek | 2024-03-06 | 2024-05-08 | 63 | 100%
2 | Financial Transactions
2.1 | Deposit cash with receipt generation. | Filip Obajtek | 2024-03-20 | 2024-04-05 | 16 | 100%
2.2 | Withdraw cash with real-time balance update. | Filip Obajtek | 2024-03-20 | 2024-04-06 | 17 | 100%
2.3 | Transfer funds between different accounts within the same bank. | Filip Obajtek | 2024-04-03 | 2024-04-16 | 13 | 100%
2.4 | Implement transaction history with filters (date, type, amount). | Ben Webb | 2024-04-10 | 2024-04-17 | 7 | 100%
3 | Account Services
3.1 | View detailed account information, including current balance, recent transactions, and account type. b. Request and manage services like | Filip Obajtek | 2024-02-17 | 2024-04-16 | 59 | 100%
3.2 | Request and manage services like checkbooks and debit/credit cards. | Chukwuma Ajoku |  |  |  | 0%
3.3 | Set up and manage recurring payments and direct debits | Chrismario Zahi |  |  |  | 0%
4 | Security and Compliance
4.1 | Implement robust authentication mechanisms (e.g., two-factor authentication). | Chrismario Zahi & Chukwuma Ajoku | 2024-04-28 | 2024-05-05 | 7 | 50%
4.2 | Ensure data encryption for sensitive information. | Chrismario Zahi & Chukwuma Ajoku | 2024-04-03 | 2024-04-09 | 6 | 100%
4.3 | Comply with relevant financial regulations and data protection laws. | Ben Webb | 2024-04-03 | 2024-04-09 | 6 | 100%